## Feature list
Feature ID | Site | Module | Screen name | API | Feature | Actor / Role | Requirement Refs | Wireframe Refs | Priority | Risk Level | Complexity | In Scope? | Confidence | Notes / Assumptions
FEAT-001 | User | Authentication | Login |  | Login | User | REQ-001 | WF-LOGIN-01 | High | High | Medium | Yes | 50%
FEAT-002 | User | Authentication | Login |  | Password reset | User | REQ-002 | WF-LOGIN-02 | Medium | Medium | Medium | Yes | 100%
FEAT-003 | Admin | User Management | Create user |  | Create user | Admin | REQ-010 | WF-ADMIN-01 | Critical | High | High | Yes
FEAT-003 | Admin | User Management | User Management |  | Assign user role | Admin | REQ-011 | WF-ADMIN-02 | Critical | High | High | Yes

## Input readiness
Feature ID | Feature name | Input Needed | Status | Current status | Next Action | Owner
|  | Project context | Ready |  |  | QC
FEAT-001 | Login | Feature spec/Use case document. | Ready | Use case is ready/finalized. | Wait to the wireframe finalized. | BA
FEAT-001 | Login | Wireframe/Design files. | Partial | Wireframe are 1/2 ready. There are missing Login successfully screen. | Wait to the wireframe finalized. | BA
FEAT-002 | Password reset | Feature spec/Use case document. | Ready | Use case is ready/finalized. | Test scenarios and test cases design. | BA
FEAT-002 | Password reset | Wireframe/Design files. | Ready | Wireframe are ready/finalized. | Test scenarios and test cases design. | BA

## Test design status
Feature ID | Feature name | Tc .md status | Tc .xlsx status | Current .md status | Current .xlsx status | Next Action | Owner
FEAT-001 | Login | Partial | Missing | Written 10/50 test cases. | Not start yet | Complete .md file. | QC
FEAT-002 | Password reset | Ready | Missing | Writted 100/100 test cases. | Not start yet | Write .xlsx file. | QC